## Instruction -Anweisung APPR
Instructions for completing AIXTRON APPR Report
2
Element-No | Element Name | Explanation | Example of Achievement | Responsible
1.1 | Non-Disclosure Agreement (NDA)* | Prior to any activity which will be executed, a non-disclosure agreement (NDA) between AIXTRON and supplier, must be agreed and signed by both parties. | - signed document from both sites | AIXTRON
1.2 | Supplier self-disclosure* | The supplier self-disclosure collects the important charaterisitcs, which AIXTRON needs to know from their supplier base. | - submitted document by supplier | Supplier
The self-disclosure is the first assessment of the supplier, to ensure his ability to handle and match the AIXTRON requirements and provide an indication of its economic strength.
The more the data will be provided by the suppliers, more reliable is the assessment that will help built the frist stage of the business relatiionship between AIXTRON and the supplier.
1.3 | Access to External-Data-Exchange System (EDE) | AIXTRON use the External-Data-Exchange method to share all relevant informations with the suppliers. The system can be access via Internet and provided link + access data provided by AIXTRON. | - known access at the Supplier | AIXTRON
1.4 | Communication Matrix* | The communication matrix is a tool to support, streamline and visualise the communication and informationsflow between the business partners. | - submitted document by supplier | AIXTRON
It also contains informations about the contact details of the defined deputies and from the escalation levels.
2.1 | Request for quotation (RFQ) with FSR | The goal is that, through RFQ's for new products, the suppliers already get knowledge about the requirements to provide a FSR (First Sample Report). | - RFQ sent to supplier | AIXTRON
The FSR process requires time and efforts, which needs to be considered as early as possible, to ensure the correct calculation of required lead time.
2.2 | Technical documentation available in full* | Aixtron is obliged to provide the following data to the suppliers: > Drawings > Full BOM > CAD (Step) models > Company standards & Work instructions > Supplementary Book of Requirments | - all relevant technical documents are known at supplier | AIXTRON
2.3 | Packaging and labeling requirements | As Aixtron is a major supplier for the Semiconductor industry, all products require some higher attention to cleanliness and packaging. | - specifications are known at supplier | AIXTRON
For a certain product commodity, it may require specific cleaning and packaging (Material & Method). This are further informations which complete the requirement package and has to be shared up front with the RFQ package.
2.4 | Customer specific test requirements | Some components inside the AIXTRON products, may require some 'special' testing. The method and procedure of those tests are described by AIXTRON and has to been provided to secure the awareness at the Supplier. | - specifications are known at supplier | AIXTRON
The Supplier then needs to assess his capabilities in order to méet the special test requierements.
2.5 | Manufacturability analysis* | Within the Elements 2.1 till 2.4 the supplier receives lot of information, requirments and specification. | -signed and submitted 'Feasibility Commitment' document | Supplier
Those inputs needs to be analysed deeply and each item, which cannot meet these inputs and achieved for 100%, needs to be listed and communicated in front of any purchase order from AIXTRON.
Received Purchase orders, for which the manufacturabilty analysis is missing or not 100% achieved, can't be accepted.
The identified gaps, has to be planned by supplier, with clear actions and timing to overcome, or needs to be discussed with AIXTRON.
This discussion has to result into redmark drawings with mid term actions, to change the requirements or the processes at supplier.
2.6 | Purchase order with FSR | For each new product and/or for new supplier, the first purchase order should contain a requirement to provide a FSR (First Sample Report). AIXTRON add dedicated and defined text module for FSR into the Purchase order. | - PO received at supplier | AIXTRON
3.1 | Design FMEA * | Only relevant for suppliers with PO including development activities The Design FMEA (DFMEA), is a risk evaluation and prevention tool. | - Design FMEA for planned product | Supplier
The major goal is to identify as early as possible the potential failures and take actions to prevent the potential failure mode will occur.
The DFMEA or Risk assessment of the Design of the product can be considered as a first Quality Gate and can solve major concern in serial phases, by low investement of time.
And by analysing the product requirement vs the planned Material, connections, required lifetime etc.
The DFMEA can also be considered as Know-How database, which helps to learn and collect knowledge
Each new developed product, assessed in an early stage by DFMEA will ensure continuously growing quality performance.
3.2 | Product Verification Plan | The Supplier will agree togerther with AIXTRON team, which inspections and tests have to be performed to ensure right product quality during FSR / Product Element. | - agreed inspections and tests as part of FSR planning | Supplier
3.3 | Concept for packaging and labeling | If a packaging concept from AIXTRON is available, it will be specified. | - proposal for product packaging submitted to AIXTRON | Supplier
In the absence of an existing concept, it is the supplier's responsibility to develop a suitable packaging concept in accordance with the AIXTRON requirements specified in 2.2 and to coordinate it with AIXTRON in advance.
3.4 | Production relevant technical specifications* | AIXTRON describes a FINISHED PART in its drawings and factory standards. The supplier is obliged (where needed) to convert these into PRODUCTION-READY DRAWINGS and INSTRUCTIONS for ist own production and machinery. | - production ready drawings and instructions created | Supplier
3.5 | Proof of concept (see 3.4) | Depending on the complexity, the documents generated under point 3.4 will be discussed with AIXTRON in advance and released if necessary. | - production ready drawings and instructions approved by AIXTRON | Supplier
3.6 | Approval of purchased material | The Supplier should ensure that purchased material is approved prior using it during FSR production. An approval requires inspection and documentatio of all relevant product characteristics. | - list of materials and suppliers with 'approved' status | Supplier
3.7 | Final AIXTRON drawing & BOM * | All relevant AIXTRON Drawings, BOM and other specifications should be checked if the final version (changes were required from element 2.5) is released and submitted to supplier. | - latest drawing revisions, BOM, specifications at supplier | AIXTRON
3.8 | Product Approval - (FSR) * | All product properties must be checked and verified against the required specifications. All measurement and evidences have to be fully documented inside the FSR (First Sample Report). | - signed and submitted FSR documentation | Supplier
AIXTRON checks the completeness and plausibility of the documents and measurements. Subsequently, AIXTRON evaluates them accordingly as *FREE* / *FREE with CONDITION* / *REJECTED*.
4.1 | Process Flow Chart | The flow chart is a visualisation instrument, to show the flow of material within the manufacturing process, including quality gates. | - production process flow chart - manufacturing Layout | Supplier
With this visualisaton, it can be easily seen the complexity and level of quality control.
4.2 | Risk Management (Process FMEA) * | The process FMEA is a tool to manage risks. The method is to identify potential failures and their consequences. This information, will be rated in terms of the following categories | - process specific FMEA - ohter method for process risk assessment analysis | Supplier
1) Probability of occurrence ==> How likely is the error to occur
2) Severity ==> What is the impact of the failure (e.g. optical appearance, loss of function)
3) Detection ==> What is the possibility to detect the failure with the current available quality gates
With those 3 evaluation a Risk priority matrix can be generated and highlighted. With this the focus of actions and potential investments can be driven
It also helps to direct the focus of quality gates definition.
4.3 | Production control plan * | This tool is a summary document to collect and visualise from the different q-gate, in accordance to the process flow chart to different quality checks. | - production control plan - overview of planned controls with frequency and evidence | Supplier
The brief summary shows the frequency of testing, if needed, link to the assigned work instruction and a reaction plan. The production control plan is also driven by the FMEA or risk prevention tool.
Main focus is to secure, that after a certain level inside the manufacturing process, the given product characterisics are confirmed, prior to any further added value.
4.4 | Work, testing and procedural instructions | Here the target is to describe the way of working. This secures the same output with a standardised operation. | - All required instructions are released into production | Supplier
The importance of this tool grows, when different people have to perform the same operations. Individualism will be eliminated.
4.5 | Personnel resource planning (e.g. qualification matrix) | The supplier has to ensure that all the resources and qualifications necessary for manufacturing have been determined. | - Qualification Matrix for production and quality operators | Supplier
The staff / employees should be qualified accordingly. If this is not the case, an appropriate training must be organized and completed before series production starts.
It must be ensured that at least 2 employees achieve the needed qualification profile for the operation.
4.6 | Material resource planning | Material resource planning includes capacity planning and make-or-buy decisions. | - List of required machines, equipment available - Visits/Audits at sub-suppliers | Supplier
Based on strategic decisions different plans to be generated (e.g. Maschinery and equipment plan, sub-contractors process approval)
4.7 | Selection and definition of unified test equipment | The supplier / manufacturer must ensure that the correct test equipment is used for the test feature. e.g. measurement of 0.1 mm deviations with a folding rule is not the right level. | - list of inspection/test equipment | Supplier
The focus is therefore on the measurement resolution of the test equipment.
If test features require a special pre-fabrication, the procurement or production must be planned in such a way that it is available, validated and ready for use at least at the start of series production.
4.8 | Process Stability | The term stability is used to describe the production process that can be repeated with the same material, equipment, and people. | - analysis of critical characteristics over time - capability evidence | Supplier
Processes tend to become unstable over time due to variations. Supplier is responsible to identify and control process variations where ever is needed.
Process stability is a tool for continues improvement and not 'one time' activity. Control charts might be used as one of possible tools.
4.9 | Lessons Learrned (Quality, Project) | Known failures, quality problems should be collected to ensure that they will be correctly addressed and prevented for running project. | - List of quality problems from past projects or products. - List of failures and problems from actual project | Supplier
In additiona, at the end of the project, the learning from failure, test and other sources have to be collected in a database, which then have to be used for any further new upcoming products out of the same commodity.
The advantage is that these type of failure and issues, will be considered / thoroughly checked in the future and will not be repeated.
So the output are more robust preparation and prevention of failures. This can be considered as another tool of risk management.
4.10 | Process Approval - (FSR) * | The correct and efficient implementation of the tools, described in the elements 4.1 till 4.7, will be evaluated by AIXTRON Supplier Quality Engineers. The evaluation method is equal to the Production part approval element 3.7. | - signed FSR for process release | Supplier
Off course in any potential coming visit of AIXTRON SQE, it will be re-checked, that the tools are still being used in the right way and documented.
General #2 | Evaluation Rules | Description of Drop-down List:
The Status of the elements can be changed through a drop-down list.
The drop-dowm list consist of status as PLANNED, IN-PROGRESS, FINISHED, N/A (Not Applicable).
PLANNED - When the closing date of an element is planned for future.
IN-PROGRESS - When the element is in the working phase.
Description of colour schemes and final calculation:
As per the status selected from the list, the ''Closing date'' can be entered in the next column.
The Colour schemes (BLACK, YELLOW, RED, GREEN) are used in the ''Closing Date'' column.
BLACK - The closing date entered is for the future after agreement with the Supplier.
YELLOW - When there are 7 days left before the agreed closing date, then the closing date will turn to YELLOW indicating the Responsible Party to work towards that particular element in order to meet the deadline.
RED - When the Responsible Party has passed the closing date agreed, then that closing date entered will turn to RED, indicating the Responsible Party to act immediately as the closing date is overdue.
GREEN - When ''Finished'' is selected from drop-down list, the closing date turns to GREEN indicating that element is fulfilled and completed.
The Element Fullfilment Degree (%) of each element is calculated in percentage, taking into account only the elements which are have the status ''Finished''.
The Overall Fulfilment of APPR is the average of the Element Fullfilment Degree (%) of each element.
General #3 | Abreviations | TQ - Technology Quality SQ - Supplier Quality CQ - Components Quality CE - Core Engineering PUR - Purchasing / Catogery Management OE - Operations Engineering / Packaging Engineer
German
English

## APPR Report
2024-08-30
AIXTRON Product & Process Readiness (APPR) Report
Supplier Information |  |  |  |  | Product Information
Supplier - Name |  |  |  |  | Product - Name
SAP Vendor Code |  |  |  |  | SAP Article - No
Order Prototypes |  |  | Date |  | Drawing & Revision Number
Order Product Qualification |  |  | Date |  | Date of drawing
Key contact information
Company |  | Name | Department |  | Phone (+XX) XXXXXX | Mail
APPR Elements / Phases
1. | Element: Commercial Fullfillments |  |  | Status | Close-Date DD.MM.YYYY | Remarks
1.1 | Non-Disclosure Agreement (NDA)* | [6 empty] | Planned | 0
1.2 | Supplier self-disclosure* | [6 empty] | In-progress | 0
1.3 | Access to External-Data-Exchange System (EDE) | [6 empty] | Finished | 0
1.4 | Communication Matrix* | [6 empty] | N/A | 0
Element Fullfilment Degree ( %) |  |  |  | 0
2. | Element: Requirement / Specification' |  |  | Status | Close-Date DD.MM.YYYY | Remarks
2.1 | Request for quotation (RFQ) with FSR
2.2 | Technical documentation available in full*
2.3 | Packaging and labeling requirements
2.4 | Customer specific test requirements
2.5 | Manufacturability analysis*
2.6 | Purchase order with FSR
Element Fullfilment Degree (%) |  |  |  | 0
3. | Element: Product Qualification |  |  | Status | Close-Date DD.MM.YYYY | Remarks
3.1 | Design FMEA *
3.2 | Product Verification Plan
3.3 | Concept for packaging and labeling
3.4 | Production relevant technical specifications*
3.5 | Proof of concept (see 3.4)
3.6 | Approval of purchased material
3.7 | Final AIXTRON drawing & BOM *
3.8 | Product Approval - (FSR) *
Element Fullfilment Degree (%) |  |  |  | 0
4. | Element: Production Process Qualification |  |  | Status | Close-Date DD.MM.YYYY | Remarks
4.1 | Process Flow Chart
4.2 | Risk Management (Process FMEA) *
4.3 | Production control plan *
4.4 | Work, testing and procedural instructions
4.5 | Personnel resource planning (e.g. qualification matrix)
4.6 | Material resource planning
4.7 | Selection and definition of unified test equipment
4.8 | Process Stability
4.9 | Lessons Learrned (Quality, Project)
4.10 | Process Approval - (FSR) *
Element Fullfilment Degree (%) |  |  |  | 0
Overall Fulfilment of APPR |  |  |  | 0
Kein offene Themen, das Projektziel wird getroffen
Offene Themen, die das Ziel geferdern, effektive Maßnahmen sind vorhanden, um das Ziel zu erreichen
Offenes Problem mit Auswirkungen auf das Ziel ohne wirksame Maßnahmen
Oder wählen Sie den Gesamtstatus aus

## Action list_Aktionlist
ACTION LIST FOR APPR Report
Supplier Information |  | Product Information
Supplier-Name |  | Product-Name
SAP Supplier Code |  | SAP Article-Nr
Order Prototypes |  | Drawing and Revision Nunber
Date
Order Product Qualification |  | Date of drawing
Date
Element No. | Action | Responsible | Date (DD-MM-YYYY) | Status %